## Academics
Responsible: person who performs an activity or does the work (The person responsible can also be accountable)
Accountable: person who is ultimately in charge of the task completion and in charge of the operation or project
Consulted: person that needs to provide feedback, double check work, or contribute to the task in miscellaneous ways
Resources: people, time, materials, or money that is needed to complete a project
Potential Barriers: items that can hinder the plan if not addressed
Academic Goals
| Address whether the "Capturing Kids Hearts" program aligns with the Core Virtue design in traditional-classical education and if it does, make some adjustments to the input. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Compare and contrast the character qualities in Dr. Moore's essay with the character qualities in CKH. | Ex Dir and Principals | Ex Dir and Principals | Process Champions | Dr. Moore's essay, CKH Information and Model | Budgetary constraints to purchase materials, provide training, and resources including input from auditor. | February 2025 | Having a character education program that aligns with the educational philosophy that upholds the standards of our Core Virtues will help with identity and consistency that will strengthen the character of all kids at MA
FALSE | Create consistent philosophy-based communication to all stakeholders to ensure buy-in. | Ex Dir and Principals | Ex Dir and Principals | Auditor Input | Clear philosophy | Ensuring consistent understanding for all staff. | January 2025 | Clarity decreases adversity and anxiety.
FALSE | Create the criteria for approval of educational materials that align with the MA philosophy, vision, mission, and revisit the current policies. | Ex Dir and Principals | Ex Dir and Principals | Auditor Input | 7 Tenets | Time and Personnel | March 2025 | This will serve as the measure that helps create the rubric tools used to evaluate instructional material.
FALSE | A solidified objective measure or rubric that provides guidance to prevent confusion or any deviation from the philosophy. | Ex Dir and Principals | Ex Dir and Principals | Dir of Academics | Consistent Rubric Layout | Time and Personnel | March 2025 | The objective measure will create accountability and help to enforce adherence to character education in relationship to the philosophy.
FALSE | Create replicable training for new teachers to MA | Principals | Principals | Dir of Academics | Slide deck, professional development, and daily implementation and buy-in | Money and time for PD | July 2025 | This will provide long-term consistency and foundational applications and implementations of our agreed upon character education curriculum. Daily application and buy-in is the most effective form of on-going professional development.
| Establish the criterion for any approved educational material (includes text and any supplements). | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Create the criteria for approval of educaitonal materials that align with the MA philosophy, vision, mision, and revisit the current policies. | Principals and Academics Dir | Principals | Executive Director | Clear philosophy and current policies | Time | March 2025 | Ensuring all supplemental materials align and support the philosophy based curriculum will increase fidelity and improve practice.
FALSE | Create a timeline for the creation of a rubric, the review of material, and the removal and/or implementation of any new instructional supplements and tools. | Principals and Academics Dir | Principals | Curriculum Committee | Scheduling meetings and providing the time to create and execute the plan that results with a product. | Time and Personnel | February 2025 | Timebound objectives increase productive and prioritization.
FALSE | Create and deliver clear communication that provides the rationale for instructional materials used to promote buy-in and understanding. | Principals | Principals | Executive Director | Clear philosophy and understanding of the 7 Tenets | Time and Personnel | February 2025 | Clarity decreases adversity and anxiety.
FALSE | Create a rubric that provides objective guidance to prevent confusion or deviation from the philosophy. | Principals and Academics Dir | Principals | Curriculum Committee | Consistent Rubric Layout | Time and Personnel | March 2025 | Ensures a tool is in place that provides objective guidelines. This creates consistency that becomes part of the foundational replication of excellence.
| Training in Monument Academy Educational Philosophy and Core Knowledge for the entire staff. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Provide comprehensive training to new teachers and staff members that defines the philosophy and provides a common ownership in MA's mission and vision. | Principals and Academics Dir | Principals | Executive Director | A well designed presentation that could be replicated for teachers who come in midyear. | Time, Money, Personnel | August 2025 | The outcomes for this will increase teacher understanding of what they teach, help create accountability measures for how they teach, and ensures alignment that supports the mission and vision that extends from preschool to 12th grade.
FALSE | Provide on-going training to current teachers and staff members to help maintain consistency each year and realign objectives and goals to support MA's mission and vision. | Principals and Academics Dir | Principals and Academics Dir | Executive Director | A well designed presentation that can be replicated each year and updated as needed withouth detracting from the primary purpose. | Time, Money, Personnel | August 2025 | This will help increase teacher retention and support.
FALSE | Provide training that explains the chosen curricula, how we use it, and apply it back to the philosophy of why we use it. (New and returning staff) | Principals and Academics Dir | Principals | Executive Director | On-going updated professional development that stays on track with chosen parts to the curriculum that does not sway from the original philosophy. | Time, Money, Personnel | August 2025 | This will create the rationale that helps drive the expectation of excellence and adhering to the curriculum with fidelty.
| Review of supplemental curriculum to identify if the program is essential. If the supplemental curriculum meets expectations, then order. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Yearly review of any teacher desired instructional materials, tools, supplements etc by curriculum committee. | Curriculum Committee | Curriculum Committee | Teachers/Team Leads | Instructional Material/Curriculum Rubric | Time | March 2025 | Proper instructional material being reviewed and ordered in a financially responsible manner.
FALSE | Clear communication to staff including initial parameters, deadlines, and budgetary constraints | Curriculum Committee | Curriculum Committee | Finance Director | Communication to staff that provides the rubric, the deadlines, and individual department budgets. | Time | March 2025 | Full understanding and expectation of the ordering process within the needed financial timeline.
| Training in administration on Core Knowledge at the National Core Knowledge National Conference. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Provide proper training for administrators to ensure they understand the scope and sequence, the standards, the best practice for implementation, and the way the curriculum fits into our philosophy | Ex Dir and Principals | Ex Dir and Principals | Finance Director | Research to find affordable and appropriate training for adminstrators that fits into the budget and meets the needs of our adminstrative team to comprehensively understand the curriculum. | Budget, Time, and Access to PD | June 2025 | We need well informed administrators to lead our staff in how to implement and utilize the curriculum for the best possible academic outcomes for students.
FALSE | Enhance evaluation tools to better support teachers in delivering the instructional materials to increase student achievement | Principals | Principals | Ex Director and Dir of HR | Alignment between curriculum standards of best practice and evaluation tools. | Time and effective implementation | June 2025 | Educated, Informed, Supported, and Accountability teachers
FALSE | Enhance evaluation tools to provide more accountability for instructional staff to deliver the curriculum uses best practice and high delivery performance to increase student achievement. | Principals | Principals | Ex Director and Dir of HR | Alignment between curriculum standards of best practice and evaluation tools. | Time and effective implementation | June 2025 | Educated, Informed, Supported, and Accountability teachers
FALSE | Enhance administrator evalutaion tool to provide Executive Director more objective measures to hold administrators accountable for teacher performance and student outcomes. | Executive Director | Principals | Ex Director and Dir of HR | Alignment between curriculum standards of best practice and evaluation tools for principals to support and lead teachers. | Time and effective implementation | June 2025 | Educated, Informed, Supported, and Accountability principals
| Creation of a two-year professional development calendar based on data, philosophy, and educational practices | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Result
FALSE | Analysis of past professional development- what has worked and what has not and what aligns with our philosophy. Creating a research based plan that has high success outcomes. | Ex Dir and Principals | Principals and Academics Dir | Teachers/Team Leads | Comphrensive list of previous PDs, assessment of their impact (negative or positive), and comparing them with research-based plans that show positive outcomes. Assessing alignment of past PDs with philosophy. | Time and personnel | April 2025 | Achieves the best practice of beginning with the end in mind, and planning for longevity and continued education that truly increases teacher performance and positive student outcomes.
FALSE | Identify areas of needed growth for our instuctional practices and create professional development that provides education, tools, and resources to teachers that aligns with our curriculum and philosophy | Principals and Academics Dir | Executive Director | Teachers/Team Leads | Review overall teacher performance evaluations and ratings, review student achievement and growth data, review current expectations and evaluations to determine an accurate guide to identify needed areas of growth. Will need to prioritize high to low needs of growth in instructional delivery and curriculum understanding and implementation. | Time, budget, personnel, data collection and accuracy/application | March 2025 | Our alignment to the philosophy and the clarity for curriclum and instructional delivery expectations will increase accountability and ownership.
FALSE | Creating a two-year budget that will allow for on-going professional development. | Principals and Finance Dir | Executive Director | Dir of Academics | Work with finance to determine the allotted amount for the first year and the projected amount for the second year when yearly budgets go under review. Keeping track of expenses and allocating funds appropriately. | Budget and proper projections | March 2025 | Having a clear plan and building the budget for the plan alleviates stress, creates urgency to make sure that the plans implemented will reach a certain point to provide continuity for the upcoming school year.
FALSE | Creating professional development foundations that will establish year-to-year consistency even with any teacher turn-over | Dir of Academics | Executive Director | Principals | Tracking which teachers have done which trainings, and having consistent new teacher trainings that keep them up-to-date and instep with current instructional staff. | Consistency and follow-through | June 2025 | These trainings will be the foundation of who Monument Academy is and what we do. Once these essential trainings are established, this will provide an opportunity to improve the trainings year over year.
| Staff Professional Development – Core Knowledge, Cursive First (PK-5), Focus (PK–12), MA Philosophy and instructional practices. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Result
FALSE | Create documented vertical alignment checklists to use as a reference tool for content and pacing | Dir of Academics | Principals | Staff | Vertical alignment checklist that coincides with curriculum standards and philosophy. | Time, consistency, buy-in, and personnel | July 2025 | Creation of a vertical alignment document ensures that students are receiving instruction that does not miss out on any area of foundational skills throughout the student's educational journey.
FALSE | Create a budget and a professional development calendar that allows for intentional and in-depth training for all curricula used for grade level and content area staff | Principals and Finance Dir | Executive Director | Dir of Academics | Detailed budget with proper budget codes and a preplanned calendar that prioritizes needs within the contsraints of time. | Time, Budget, personnel, data collection and accuracy/application | March 2025 | Professional development can be an expensive working with different instructional companies. This discussion will be held on what we can conduct ourselves versus where the school should connect with an outside expert.
FALSE | Provide consistent, coherent, and impactful teacher professional development that aligns with teacher performance expectations to ensure accountability measures can be utilized | Principals and Academics Dir | Principals | Ex Director and Dir of HR | A clear document that shows what they are learning and how it will be measured and evaluated. Provide the expectations that align with the training. | Time, Budget, personnel, data collection and accuracy/application | June 2025 | With administration and staff on the same page of how a program is expected to implemented, this will provide accountability for everyone involved.
FALSE | Providing clear communication that explains the who, what, when, where, and why to increases teacher buy-in and participation | Principals | Executive Director | Dir of Academics | Written communication that supports the why to increase buy-in. | Time and personnel | February 2025 | Clarity decreases adversity and anxiety.
| Provide clear objectives for each curricula that aligns with performance evaluations and student growth and acheivement | Principals and Academics Dir | Ex Dir and Principals | Dir of Academics | Best practice modeled- Learning Objectives, Success Metrics, Clear Expectations, Outcomes/Producibles, and Celebrations | Time and personnel | June 2025 | Leadership can model best practice for teachers to replicate by utilizing objectives, standards, and assessment evaluations.

## Board
Responsible: person who performs an activity or does the work (The person responsible can also be accountable)
Accountable: person who is ultimately in charge of the task completion and in charge of the operation or project
Consulted: person that needs to provide feedback, double check work, or contribute to the task in miscellaneous ways
Resources: people, time, materials, or money that is needed to complete a project
Potential Barriers: items that can hinder the plan if not addressed
Board
| Evaluate the Strategic Plan to determine alignment to action plan from audit. Amend anything that is counterproductive and add any new facets that need to be addressed. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Ensure the Strategic Plan Aligns with Monument Academy Philosophy, Mission, and Vision | Board of Directors | Board of Directors | Staff |  |  | 2025-01-01
FALSE | Create Consistent Process When Creating Strategic Plans and All Items Are Defined | Executive Director | Board President |  |  |  | 2025-06-01
FALSE | Provide Definitions/Reasons Certain Words are Chosen in the SWOT and How They Are Connected to the Mission, Vision, and Philosophy | Board of Directors | Board of Directors |  |  | Clarity in the process
| To ensure that the future of MA is secure in academics and programs, compose and vote on policies pertaining to Educational Philosophy, Penmanship Philosophy, Class Size (including kindergarten), Curriculum Approval Criterion, and identify policies of immediate concern. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Compose Policy About Educational Philosophy | Board of Directors | Board of Directors | Staff | Mission, vision, philosophy / charter applications / academic tools understanding | Frameworks created vertically and horizontally in high school and fine arts | 2025-03-01
FALSE | Compose Penmanship Philosophy | Board of Directors | Board of Directors | Staff | Evidence-based information on Cursvie First | Transfer students / understanding the why | 2025-03-01
FALSE | Review Class Size Policy | Board of Directors | Board of Directors | Executive Director | Colorado Revised Statutes / charter application / room capacity | Space / staffing / personnel cost vs. budget / educational resources | 2025-02-01
FALSE | Review Curriculum Approval Policy for Primary and Supplemental Materials | Governance Committee | Board of Directors | Dir of Academics | Mission, vision, philosophy | Time | 2025-03-01
FALSE | Identify Policies of Concern | Governance Committee | Board of Directors | Executive Director | Policies | Mission, vision, philosophy understanding and knowledge | 2025-02-01
| Board Training – Board roles, responsibilities and academic programs of Monument Academy | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Develop a Training Module on Board Governance Aligned with Monument Academy's Vision | Board of Directors | Board President | Executive Director | Expert consultant / materials / board philosophy | Scheduling / understanding on different philosophies | 2025-06-01
FALSE | Conduct Professional Development on the Academic Programs and How the Programs Align with Monument Academy Educational Philosophy | Executive Director | Board of Directors |  | Expert consultant / academic reports / case studies |  | 2025-07-01
FALSE | Facilitate Discussion on Improving Student Outcomes Through Board Decisions | Executive Director | Board of Directors | Principals | Relevant performance data / meeting space / guided questions | Low engagement | 2025-06-01
FALSE | Teacher Representatives to the School Board | Principals | Board of Directors | Executive Director |  | Low engagement | 2025-06-01
| Update new Board member training | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Develop a Training Module Emphasizing the Importance of Respect, Responsibility, and Willingness Toward Shared Goals. | Executive Director | Board of Directors | Board President | Training materials / mission, vision statements | Time
FALSE | Provide all information for standard yearly board member training | Board President and Ex Dir | Board President | Board of Directors | Topic materials
FALSE | Provide training for legal responsibility and policy awareness and understanding | Board President and Ex Dir | Board of Directors | Legal | Created materials
FALSE | Organize Classroom Observation Days for New Board Members at All School Levels: Elementary, Middle School, and High School | Executive Director | Board of Directors | Principals | Classroom schedules / observation guidelines / principal introductions | Time / board buy in / teacher buy in | 2025-08-01
| Audit Team Review of Progress | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Creation of a Rubric to Review Success of Plan | Leadership Forum | Executive Director |  | Educational philosophy / personnel expertise
FALSE | Leadership Forum Review of Progress | Leadership Forum | Board of Directors |  | Rubric / documentation / personnel expertise | Bias in the review process | Quaterly

## Executive
Responsible: person who performs an activity or does the work (The person responsible can also be accountable)
Accountable: person who is ultimately in charge of the task completion and in charge of the operation or project
Consulted: person that needs to provide feedback, double check work, or contribute to the task in miscellaneous ways
Resources: people, time, materials, or money that is needed to complete a project
Potential Barriers: items that can hinder the plan if not addressed
Executive
| Development of an aggressive marketing plan focused on enrollment for the 25-26 and planning for 26-27 school year. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Define Specific Enrollment Goals by Grade Level and Total Numbers | Principals | Executive Director | Registrar | Enrollment Data from choice window and Intent to Return |  | 2025-03-01 | Skills and Resources
FALSE | Analyze the Effectiveness of Current Marketing Strategies and Community Engagement Efforts | Marketing Committee | Executive Director |  | Marketing data, enrollment surveys |  | 2025-05-01 | Does the school have the required skills and staff to execute the marking plan, or should a marketing firm be considered?
FALSE | Gather Enrollment Data, Including the Number of New Enrollments Per Grade Level Annually | Registrar | Executive Director | Principals | Enrollment data | Communication from families | 2025-06-01 | Are there opportunities to train existing staff to manage specific aspects of the campaign (e.g., social media or SEO)?
FALSE | Assess the Current Environment, Including Competitive Positioning and Demographic Trends | Marketing Committee | Executive Director | Administration Team | School data for the community |  | 2025-07-01 | Budget and Funding
FALSE | Identify Target Demographics (e.g., Families in Specific Areas In/Out of the District). | Marketing Committee | Executive Director | Principals |  |  | 2025-08-01 | What is the allocated budget for the marketing plan, and is it sufficient to achieve enrollment goals?
FALSE | Assess Competitors' Offerings and Market Position | Marketing Committee | Executive Director |  | School data for the community |  | 2025-09-01 | Are there external funding opportunities or grants that could support marketing efforts?
FALSE | Highlight Unique Selling Points (e.g., Curriculum, Extracurriculars, Faculty Expertise). | Marketing Committee | Executive Director | MA Community |  |  | 2025-10-01 | Timeline and Milestones
FALSE | Create a Compelling Narrative/Elevator Pitch About the School's Value | Marketing Committee | Executive Director | Principals |  |  | 2025-11-01 | Are the proposed timelines realistic, given the school's operational capacity?
| Leverage Digital Platforms (e.g., Social Media, Google Ads). | Marketing Director | Executive Director | Marketing Committee | Social media accounts | Streamlining the process for social media | 2026-01-01 | How will progress be monitored and adjusted throughout the implementation period?
FALSE | Establish a New Marketing Plan, Including Search Engine Optimization (SEO), Radio, and Social Media. | Marketing Director | Executive Director | Marketing Committee |  |  | 2026-02-01 | Post-Implementation Evaluation
FALSE | Utilize Traditional Methods Like Community Events, Flyers, and Local Advertising. | Marketing Committee | Executive Director | MA Community |  |  | 2026-03-01 | What metrics will be used to evaluate the success of the marketing campaign?
FALSE | Partner with Local Organizations, Host Open Houses, and Offer School Tours | Administration Team | Executive Director | Marketing Committee |  |  | 2026-04-01 | How will insights from this campaign inform future efforts?
FALSE | Collect Testimonials From Current Students and Parents | Marketing Committee | Executive Director | Administration Team |  |  | 2026-05-01
FALSE | Map Out Activities, Including Deadlines for Content Creation, Campaigns, and Events. | Marketing Director | Executive Director | Marketing Committee |  |  | 2026-06-01
FALSE | Identify Budget Requirements, Staff Involvement, and External Services Needed (e.g., Graphic Design) | Marketing Committee | Executive Director | CFO, Finance Dir |  |  | 2026-07-01
FALSE | Test Strategies on a Smaller Scale Before Full Implementation | Administration Team | Executive Director | Marketing Committee |  |  | 2026-09-01
FALSE | Track Enrollment Inquiries and Campaign Performance. | Registrar | Executive Director | Marketing Committee | Enrollment data |  | 2026-09-01
FALSE | Adjust Strategies Based on Effectiveness and Feedback. | Marketing Committee | Executive Director | MA Community |  |  | 2026-10-01
FALSE | Assess Success Against the Goal | Marketing Committee | Executive Director | Registrar |  |  | 2026-10-01
FALSE | Gather Insights to Improve Future Marketing Efforts | Marketing Director | Executive Director | MA Community | Marketing data |  | 2025-07-01
| Evaluate all leadership and administrative positions and determine each individual's effectiveness in their position and alignment of future pursuits to put Monument Academy back in conjunction with their charters and philosophy. Make any needed changes in an appropriate and prompt manner. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Define Clear Standards for Assessing Effectiveness and Alignment with the School's Charters and Philosophy | Executive Director | Executive Director | Dir of Human Resources |  |  | 2025-01-01
FALSE | Evaluate Each Leadership Position Against the Established Criteria | Administration Team | Executive Director | Dir of Human Resources | Rubrics for each position |  | February 2025 / April 2025
FALSE | Collect Input from Staff, Students, and Parents on Leadership and Administrative Effectiveness | SAAC Committee | Board of Directors | Executive Director | Survey |  | 2025-04-01
FALSE | Analyze the Evaluation Results to Ensure Alignment with the School's Future Pursuits and Philosophy | Administration Team | Executive Director | Dir of Human Resources |  |  | 2025-05-01
FALSE | Create A Plan to Address, If There Are Any Misalignments or Necessary Changes in Leadership or Administrative Roles | Executive Director | Executive Director | Dir of Human Resources |  |  | 2025-06-01
FALSE | Make Necessary Adjustments to Roles or Presonnel Promptly and Appropriately. | Executive Director | Executive Director | Dir of Human Resources |  |  | 2025-07-01
FALSE | Track the Effectiveness of Implemented Changes and Make further Adjustments as Needed | Administration Team | Executive Director |  |  |  | 2025-09-01
| Implement the components of the high school charter contract into practice for the upcoming school year. Provide an implementation plan for the Executive Director (who may share with the board). | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Conduct a Thorough Review of the High School Charter Contract to Identify Key Components for Implementation. | HS Implementation Team | Executive Director | Staff | Charter Application | Financial resources and time resources. | 2025-01-01 | This will take some time to implement over time as there are so areas that will need to change course.
FALSE | Create a Framework Outlining the Steps and Resources Needed to Integrate Charter Components Into Practice | HS Implementation Team | Executive Director | Administration Team | Framework | Time, financial, student numbers | 2025-02-01
FALSE | Collaborate with Teachers, Parents, and Board Members to Gather Input and Align Priorities | Principals | Executive Director | MA Community |  | Time resource | 2025-03-01
FALSE | Identify and Allocate the Necessary Resources, Including Budget, Staffing, and Materials | Principals | Executive Director | CFO, Finance Dir | Budget, materials | Prioritization of resources | 2025-03-01 | What should come first, and what can wait? If there is a conflict, how does the team reach a consensus on what should be prioritized?
FALSE | Design Training Sessions for Staff to Ensure Understanding and Readiness for Implementation | Dir of Academics | Executive Director | Principals |  |  | 2025-04-01
FALSE | Test Selected Components of the Charter Contract in a Controlled Environment to Identify Potential Challenges | Dir of Academics | Principals | Staff | Charter Application |  | 2025-05-01
FALSE | Implement All Components of the High School Charter Contract Into Practice. | Administration Team | Executive Director | MA Community | Charter Application | If current practices conflict with the charter contract | 2025-07-01
FALSE | Track the Progress and Effectiveness of the Implementation, Making Adjustments as Needed. | Administration Team | Executive Director | Staff | Rubric, feedback | Clear and agreed-upon criteria for what success looks like | 2025-07-01 | Identifying what success looks like in the first year and the following years.
| Implementation of a 9-session induction program for all new staff that provides in-depth training of Monument Academy’s philosophies and expectations. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Review Existing Practices and Determine Gaps in Onboarding for New Staff. | Dir of Academics | Principals | Executive Director | See Hire/Onboarding for HR |  | 2025-02-01
FALSE | Create a Structure for a 9-Session Program Focusing on Monument Academy's Philosophies and Expectations | Principals and Academics Dir | Executive Director | Staff | Philosophy | Resources for the desired tools to involve in the training. | 2025-06-01 | Understanding what tools align with the training to provide a greater depth for new teachers.
FALSE | Outline Specific Session Topics, Such as the School's Mission, Teaching Philosophies, and Behavioral Expectations | Principals and Academics Dir | Executive Director | Staff | Technology | User competence with technology, training will not fit all individual scenarios | 2025-03-01
FALSE | Explore Opportunities to Reinstitute an Induction Program For Newly Licensed Teachers, Including Costs and Feasibility | Dir of Academics | Executive Director | CFO, Finance Dir | Application for the state |  | 2025-06-01 | Discussion with the district and the state.
FALSE | Create Materials, Presentations, and Activities for Each Session of the Induction Program | Ex Dir and Principals | Principals |  |  |  | 2025-06-01
FALSE | Test Initial Sessions with a Small Group of New Hires to Gather Feedback and Make Adjustements | Principals and Academics Dir | Principals | Staff |  |  | 2025-09-01
FALSE | Evaluate the Program's Effectiveness and Gather Input for Improvements After Each Cohort Completes Induction | Principals and Academics Dir | Executive Director | Staff | Feedback form, participants of program |  | Annually

## Finance
Responsible: person who performs an activity or does the work (The person responsible can also be accountable)
Accountable: person who is ultimately in charge of the task completion and in charge of the operation or project
Consulted: person that needs to provide feedback, double check work, or contribute to the task in miscellaneous ways
Resources: people, time, materials, or money that is needed to complete a project
Potential Barriers: items that can hinder the plan if not addressed
Finance
| Develop a budget that reflects the priority areas in the audit and action plan. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Share Audit Recommendations and Action Plan with the Financial Team | Executive Director | Executive Director |  | Audit / action plan |  | 2024-12-01
FALSE | Administration & Finance Team Meeting to Prioritize Financial Needs of Each School | Administration Team | Executive Director | Staff | Financial knowlege / curriculum needs | Enrollment and PPR | 2025-02-01
FALSE | Communication for the Request of Ordering of Core Curriculum and Supplemental Curriculum | Curriculum Committee | Principals | Ex Dir, Finance Dir |  |  | 2025-03-01
FALSE | Identify Student Enrollment Count to Determine Projected Budget | Registrar | CFO | Finance Director | Intent to Return data / choice enrollment information | Will fluctuate through August | 2025-03-01
FALSE | Determine Budget for Marketing Strategies and Prioritize with Academic Needs | Marketing, Ex Dir, Finance Dir | Executive Director | CFO, Finance Director | Budget / marketing plan / school schedule of events | Lots of Needs and Limited Budget
| Create Curriculum/Classroom Budget including timeline and deadlines for submitted orders. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Inventory of Current Curriculum | Curriculum Committee | Principals |  | Inventory sheet | Finding curriculum and understanding the timeframe of curriculum | 2025-03-01
FALSE | Order Approved Curriculum | Finance Team | Principals |  | Finances, orders | Delays, money, time | 2025-07-01
FALSE | Communicate Deadlines with Staff On When Curriculum Must Be Purchased | Executive Director | Executive Director | Principals |  | Lack of planning | 2025-01-01

## Human Resources
Responsible: person who performs an activity or does the work (The person responsible can also be accountable)
Accountable: person who is ultimately in charge of the task completion and in charge of the operation or project
Consulted: person that needs to provide feedback, double check work, or contribute to the task in miscellaneous ways
Resources: people, time, materials, or money that is needed to complete a project
Potential Barriers: items that can hinder the plan if not addressed
Human Resources
| Simplify / Clarify Organizational Chart | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Simplify Organizational Chart | Ex Dir, Ops Dir, HR Dir | Dir of Human Resources |  | Organizational chart |  | 2025-01-01 | A simplified organization chart provides clarity for supervisors and supervisees. It reflects the order of operations and chain of command.
FALSE | Add Links to the Organizational Chart with Job Descriptions | Dir of Human Resources | Dir of Human Resources |  | Organizational chart / job descriptions |  | 2025-03-01 | Clarity decreases adversity and anxiety.
FALSE | Create Departmental Organizational Charts | Ex Dir, Ops Dir, HR Dir | Dir of Human Resources |  | Organizational chart |  | 2025-03-01 | Creating microcosms within the organization also provides more clarity for departments within the school.
FALSE | Educational Meeting with Staff to Discuss the Different Roles and Answer Questions | Dir of Human Resources | Executive Director | Staff | Informative Presentation and Clear Explanation of the Who, What, Why | Engagement | 2025-08-01 | We want input and feedback to help create an organizational chart that all stakeholders can understand and uitlize.
| Develop a hiring and onboarding program for new hires that includes philosophy and values of Monument Academy. Include the use of Core Knowledge and traditional-classical education. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Refined Job Descriptions that Include Educational Philosophy | Dir of Human Resources | Dir of Human Resources | Executive Director | Job descriptions / policy |  | 2025-03-01 | To find employees who adhere to the philosophy and meet the expectations of Monument Academy. The hiring process will become the first step in getting the right people into our organization.
FALSE | Refine Interview Questions That Focus on Monument Academy Educational Philosophy | Hiring Advisory Team | Dir of Human Resources | Principals | Educational philosophy | Narrowing priorities in communicating with staff | 2025-02-01 | We need pin pointed questions that help us find the best of the best when we are looking for employees.
FALSE | Update Interview Process Including Involving Parents, Candidates Teaching Lessons, and Candidate Reflection | Hiring Advisory Team | Executive Director | Dir of Human Resources | Training / classroom time / lesson plans / | Size of hiring pool / time / training parents before hiring window opens / no qualified candidates apply for the position | 2025-03-01 | Parent participation increases ownership in teacher performance, accountability, and expectations. Teachers need to be involved in the selection process of their colleagues. Having a well informed hiring committee is the first step in finding individuals who align with the mission, vision, and ultimately philosophy at MA.
FALSE | New Hire Letter (Champion Letter) | Ex Dir, HR Dir | Executive Director | Principals |  | Staff or potential hires that don't agree to the document | 2025-01-01 | Providing the expectations right out of the gate before a person accepts a job at MA will allow us to hold people more accountable after he/she chooses to join our team.
FALSE | Welcome to Monument Academy Video to Help New Hires with On-Boarding Information | Human Resources Department | Executive Director |  | Technology / programs / handbook |  | 2025-08-01 | We need to have ways of training individuals mid-year, so we can hold all hires accountable to what we expect and need from all employees. The information will be updated each year. This will also help us train substitutes, so they are informed and can be held accountable for performing to the standards of MA excellence.
| Update staff handbook to include information on philosophy (including the Penmanship Philosophy), instructional practices and expectations for the classroom. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Refine Handbook to Align with Educational Philosophy | Ex Dir and HR Director | Executive Director | Principals | Handbook / policies |  | 2025-04-01 | The staff handbook will reflect the core values and philosophy of the school, which will drive the expectations, accountability for staff conduct, and the school's character.
FALSE | Administration Team Reflection on Changes or Gaps in the Handbook from Previous Years' Experience | Administration Team | Executive Director | Dir of Human Resources | Handbook | Differing opinions | 2025-04-01 | Staff must understand the expectations in order for the supervisors to hold them accountable.
FALSE | Input From Principals for Expectations and Procedures that Align Between Campuses | Principals | Executive Director | Dir of Human Resources | Areas of needed clarity |  | 2025-04-01 | Consistent application and enforcement must be established to ensure the code of conduct and integrity of the collective character of MA is upheld.
FALSE | Legal Review | Legal Team | Dir of Human Resources |  |  |  | 2025-05-01 | We will be compliant with all labor laws and any state and federal laws that direct our decision making and enforcement of policies.
FALSE | Presentation to Staff Followed by a Question and Answer Session to Make Everyone Aware of the Focus Points and Provide Clarity | Dir of Human Resources | Executive Director |  | Handbook / presentation | Engagement and Accountability | 2025-08-01 | The principals will be well versed in the handbook expectation and policies. Human Resources provides support to leadership in the enforcement of the policies; however, direct supervisors are responsible for understanding how to hold their staff accountable.
| Create a cohesive and clear student handbook between West and East Campus, that reflects Monument Academy’s philosophy and values and doesn't contradict the staff handbook. | Responsible | Accountable | Consulted | Resources | Potential Barriers | Deadline | Notes
FALSE | Refine Handbook to Align with Educational Philosophy | Administration Team | Executive Director | Dir of Human Resources | Handbook / policies |  | 2025-04-01 | The student handbook will reflect the core values and philosophy of the school, which will drive the expectations and accountability for the student's conduct and the school's character
FALSE | Cross-Referencing Staff Handbook Between Policy and Alignment and Discussions with Principals on Best Practices | Administration Team | Executive Director | Dir of Human Resources | Handbook | Conflicting information | 2025-04-01 | The teachers will be well versed in the handbook expectation and policies. Supervisors provide support to teachers in the enforcement of the policies; however, teachers and student-facing staff are responsible for understanding how to hold their students accountable.
FALSE | Simplification in Areas That Can Be Condensed in the Handbook | Administration Team | Executive Director | Dir of Human Resources |  | Ensuring important information is not lost in the condensing. | 2025-04-01 | This should increase clarity without sacrificing importance.
FALSE | Legal Review | Legal Team | Dir of Human Resources | Executive Director |  |  | 2025-05-01 | We will be compliant with all labor laws and any state and federal laws that direct our decision making and enforcement of policies.
FALSE | Create a Process to Bring Awareness of Key Points to Families | Principals | Executive Director | Staff | Handbook | Families wanting to engage in a large complex document | 2025-08-01 | The handbook is only as useful as it is understood and accepted by families and students. Properly informing family stakeholders increases the level of accountability that can be used to hold our students and parents to the high character expectations embraced by the MA philosophy.